## Project Summary (hidden)
Project | Budget | Actual | Forecast | Variance | % Budget Used | CPI | SPI | Status | ETC | EAC | VAC |  | SPI
Project A | 100000 | 85000 | 105000 | -5000 | 0.85 | 1.18 | 0.95 | ⚠️ Over Budget | 20000 | 105000 | -5000 | 1.1765 | 0.95238
Project B | 120000 | 90000 | 115000 | 5000 | 0.75 | 1.33 | 1.04 | ✅ On Track | 25000 | 115000 | 5000 | 1.3333 | 1.0435
Project C | 95000 | 92000 | 97000 | -2000 | 0.97 | 1.03 | 0.98 | ⚠️ Over Budget | 5000 | 97000 | -2000 | 1.0326 | 0.97938
Project D | 110000 | 100000 | 108000 | 2000 | 0.91 | 1.1 | 1.02 | ✅ On Track | 8000 | 108000 | 2000 | 1.1 | 1.0185

## Cost Breakdown (hidden)
Project | Category | Cost
Project A | Labor | 6785.13 | Row Labels | Sum of Cost | Sum of Cost | Column Labels
Project A | Materials | 43523.26 | Contingency | 2452.6 | Row Labels | Contingency | Grand Total
Project A | Subcontracts | 19038.79 | Labor | 6785.13 | Project A | 2452.6 | 2452.6
Project A | Overheads | 13200.21 | Materials | 43523.26 | Project B | 25236.29 | 25236.29
Project A | Contingency | 2452.6 | Overheads | 13200.21 | Project C | 3210.78 | 3210.78
Project B | Labor | 3476.13 | Subcontracts | 19038.79 | Project D | 15512.16 | 15512.16
Project B | Materials | 1226.48 | Grand Total | 84999.99 | Grand Total | 46411.83 | 46411.83
Project B | Subcontracts | 41223.15
Project B | Overheads | 18837.95
Project B | Contingency | 25236.29
Project C | Labor | 332.78
Project C | Materials | 56055.43
Project C | Subcontracts | 28582.11
Project C | Overheads | 3818.9
Project C | Contingency | 3210.78
Project D | Labor | 9130.54
Project D | Materials | 16347.23
Project D | Subcontracts | 33524.56
Project D | Overheads | 25485.51
Project D | Contingency | 15512.16

## Time Series Trend (hidden)
Project | Month | Actual | Budget | Forecast
Project A | 2025-01-01 | 13082 | 16666.6667 | 17500
Project A | 2025-02-01 | 27640 | 33333.3333 | 35000 | Row Labels | Actual. | Forecast. | Budget.
Project A | 2025-03-01 | 43393 | 50000 | 52500 | 2025-06-01 | 343471 | 425000 | 425000
Project A | 2025-04-01 | 57440 | 66666.6667 | 70000 | 2025-05-01 | 285303 | 354166.6667 | 354166.6667
Project A | 2025-05-01 | 72987 | 83333.3333 | 87500 | 2025-04-01 | 226075 | 283333.3333 | 283333.3333
Project A | 2025-06-01 | 87734 | 100000 | 105000 | 2025-03-01 | 171110 | 212500 | 212500
Project B | 2025-01-01 | 12975 | 20000 | 19166.6667 | 2025-02-01 | 111640 | 141666.6667 | 141666.6667
Project B | 2025-02-01 | 26781 | 40000 | 38333.3333 | 2025-01-01 | 53821 | 70833.3333 | 70833.3333
Project B | 2025-03-01 | 38970 | 60000 | 57500 | Grand Total | 1191420 | 1487500 | 1487500
Project B | 2025-04-01 | 53975 | 80000 | 76666.6667
Project B | 2025-05-01 | 68709 | 100000 | 95833.3333
Project B | 2025-06-01 | 83714 | 120000 | 115000
Project C | 2025-01-01 | 12562 | 15833.3333 | 16166.6667
Project C | 2025-02-01 | 26461 | 31666.6667 | 32333.3333
Project C | 2025-03-01 | 42099 | 47500 | 48500
Project C | 2025-04-01 | 55366 | 63333.3333 | 64666.6667
Project C | 2025-05-01 | 70245 | 79166.6667 | 80833.3333
Project C | 2025-06-01 | 83773 | 95000 | 97000
Project D | 2025-01-01 | 15202 | 18333.3333 | 18000
Project D | 2025-02-01 | 30758 | 36666.6667 | 36000
Project D | 2025-03-01 | 46648 | 55000 | 54000
Project D | 2025-04-01 | 59294 | 73333.3333 | 72000
Project D | 2025-05-01 | 73362 | 91666.6667 | 90000
Project D | 2025-06-01 | 88250 | 110000 | 108000

## Dashboard
Project A
|  | Budget | 100000
⚠️ Behind Schedule |  | Forecast | 105000
|  | Actual | 85000
15%
|  | % Budget Used | 85%
0.047619
|  | SPI | 0.95238
-0.17647
|  | CPI | 1.1765
Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Cost Breakdown
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Cost Vs Category Breakdown
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
BvFvA Breakdown
% Budget Used
SPI Index
CPI Index
Select
⚠️ Behind Schedule